## Deployment
PalletPort — first production deployment
Item | Detail
Platform | Vercel (project: clovis739-palletport)
Source | GitHub clovis739/palletport, branch main, commit b2c0480
Status | Ready (Production)
Build time | About 1m 56s
Live address | https://clovis739-palletport.vercel.app
Auto-deploy | Every push to main deploys to production
Root Directory | Empty (top of repo) — correct
Framework | Next.js, build command npm run build
Environment variables set | AUTH_SECRET, DATABASE_URL, DATABASE_URL_UNPOOLED, RESEND_API_KEY, EMAIL_FROM, EMAIL_TO, APP_URL
Environment variables missing | BLOB_READ_WRITE_TOKEN (photo uploads)

## Live Checks
Live site checks (first visit after deploy)
Path | Page | HTTP status | Response time (ms) | Size (bytes) | Notes
/ | Home | 200 | 2279 | 388330 | OK
/lots | All lots | 200 | 1701 | 419836 | OK
/c/electronics | Category page | 200 | 1238 | 245350 | OK
/new | New arrivals | 200 | 2394 | 354396 | OK
/contact | Contact | 200 | 1597 | 72507 | OK
/login | Login | 200 | 1970 | 67007 | OK
/does-not-exist | Unknown page | 404 | 2009 | 70641 | OK: real 404 page and status
/sitemap.xml | Sitemap | 200 | 1561 | 67596 | 473 links
/robots.txt | Robots | 200 | 1227 | 890 | OK
/merchant-feed.xml | Google Merchant feed | 200 | 1890 | 357 | 0 products until lots have their own uploaded photos
Pages checked |  |  | 10
Average response time (ms) |  |  | 1786.6
Note: times were measured from a browser on the first visit after deploying (cold start), several pages at once.

## To-Do
What's left before taking real orders
Edit the Status column (To do / Done). The count below updates automatically.
Task | Where / how | Priority | Status
Turn on photo uploads | Vercel → Storage → Blob → Create store, connect to this project (adds BLOB_READ_WRITE_TOKEN) | High | To do
Connect the domain | Vercel → Settings → Domains → add liquidationpalletssale.com, then add the DNS records Vercel shows | High | To do
Upgrade Vercel plan | Hobby plan is non-commercial; switch to Pro before real orders | High | To do
Change the admin password | Sign in at /login on the live site → account security | High | To do
Remove demo accounts | Admin → Customers / Staff: delete or change the password123 accounts | High | To do
Upload real lot photos | Admin → Lots: lots then appear in the Merchant feed | Medium | To do
Tasks done |  |  | 0 of 6